## Backlog
ID	Assigned Sprint	Assign To	Points	Name	Description
US00001	1	Bob	5	Create Corporate Customer	As an employee, I want to create a customer account, so that items can be rented to the customer.
US00002	1	Al	8	Lookup Customer	As an employee, I want to lookup existing customers, so that items can be rented to the customer.
US00003	1		5	Edit Customer	As an employee, I want to edit the customer data to make corrections to the data.
US00004				Create Invoice
US00005				Authenticate User
US00006				Setup LDAP
US00007				Add Rental Item to invoice
US00008				add retail item to invoice
US00009				total invoice
US00010				collect payment on invoice
US00011				Open register for the day
US00012				close register for day
US00013				send invoice to store records
US00014				register end of day report
US00015				store end of day report
US00016				create rental product	As a store admin, I want to create a rental product, so that rental items can be created. The rental product will have a name, description, hourly rate, daily rate, weekly rate, monthly rate.
US00017				create rental item	As a store, I want to create a rental item, so that the rental item will be a available to be rented. The rental item will have the key to the rental product, date purchased, date retired, manufacture, model, cost of the item.
US00018				rental item stats	As a store manager, I want date collected on a rental item statistics. Rent count, revenue generate, repair cost, number times repaired.
US00019				Usage report	As a store manager, I want an usage report, so that I can determine which items are profitable.
US00020	0			Setup Docker
	0			Setup Database
	0			Setup IDE
	0			Installer RabbitMQ